ROADMAP Your 46-Day Path from Absolute Beginner to Edge AI Engineer Raspberry Pi 4 (4 GB) + Windows laptops + two Pis + 2 hours a day (about 9 weeks at 5 days a week)

## The plan in one picture

Figure 1.  Six phases, 46 core days, and an optional Arduino UNO Q track. Red flags are the milestones you will be able to demonstrate.

| Phase | Days | What you learn | What you need |
| --- | --- | --- | --- |
| 0 Pi bring-up | 1-5 | Flash, boot, SSH, Linux basics, camera, Python + Jupyter on the Pi | Pi 4, microSD, power, laptop |
| 1 ML foundations (Colab) | 6-13 | Neurons, DNNs, CNNs, datasets, metrics, overfitting, Edge Impulse intro | Laptop + Google Colab, no Pi needed |
| 2 Fixed-function AI on the Pi | 14-26 | Image classification, object detection (SSD, FOMO), YOLO, counting objects | Camera (Pi camera or USB webcam), Edge Impulse account |
| 3 Generative AI on the Pi | 27-38 | RNN text, distillation, small language models (Ollama), RAG, agents, vision-language, audio, GPIO, IoT control | USB mic + speaker, breadboard, LEDs, button, sensors |
| 4 TinyML applications | 39-42 | Anomaly detection, keyword spotting, image apps on microcontrollers, responsible AI | Concepts only (no microcontroller board needed) |
| 5 Capstone + teaching plan | 43-46 | Your own project, write-up, and the plan to teach it to students | Whatever the project needs |
| 6 Optional: Arduino UNO Q | 47-56 | The same ideas on a different board (after you master the Pi and ML) | Arduino UNO Q (not owned yet) |

## How to use the plan

•  One day = about 2 hours. Read the tutorial, watch the animation, do the lab, then print the sketch notes and add your own comments.

•  Two Pis, two laptops: do every day twice. Pass 1 is the learning pass on one Pi (about 2 hours). Pass 2 is the consolidation pass on the other Pi, from your notes only, which should take less time. Alternate which Pi you learn on. This catches mistakes that hide behind copy-paste.

•  Name your Pis differently (for example raspi-office and raspi-home) and keep the same user name on both. Keep code and notes in the GitHub repo and use git pull, so both Pis and both laptops stay in sync.

•  Phase 1 (ML foundations) needs no Pi, only Google Colab, so it is a good block to do when you are travelling.

•  Book page numbers below are PDF pages of the book file (printed page + 1). The splits of long chapters across days are estimates; I will adjust them as we go.

CAREFUL Honest limits of this plan • Pi 4 with 4 GB: the vision chapters will run fine. The language-model chapters (Phase 3) were written for a Pi 5 and will be slower here, and only small models fit. We will choose model sizes to match your board and I will report slower-than-book results as they are. • Software versions: a newer Raspberry Pi OS may ship a newer Python than the book used, and TensorFlow Lite can be picky about that. Day 4-5 includes the check. • Online services (Colab, Edge Impulse, model downloads) need Internet access, and your office network may restrict some of them. Plan to use a phone hotspot on those days if needed. • UNO Q chapters are from a different online book and course slides that I have not read yet; the RAG classes for it are marked 'to be developed' in the course README.

## What to prepare, and when

| By day | Item | Why |
| --- | --- | --- |
| 1 | Pi 4, microSD (32 GB+), USB-C power 5 V / 3 A, card reader, Wi-Fi details | Everything in Phase 0 |
| 4 | Pi camera module (CSI) or a USB webcam | Camera test and all vision projects |
| 6 | Google account (Colab) | ML foundations |
| 13 | Edge Impulse account | Training in Phase 2 (check the current free tier) |
| 27 | Internet on the Pi for model downloads; enough free space on the microSD | Ollama and models |
| 35 | USB microphone and speaker | Audio pipeline |
| 36 | Breadboard, jumper wires, LEDs + resistors, push button, DHT temperature sensor, BMP280 pressure sensor | GPIO and sensors (the repo scripts use these; confirm the exact parts in the chapter before buying) |
| 47+ | Arduino UNO Q (optional) | Alternative hardware track |

# Day-by-day plan

C = class number in the course repositories (IESTI05 = Edge AI, IESTI01 = TinyML).  Book pp. = PDF pages of 'Edge-AI-Engineering book.pdf'.  A dash means the day is based on slides, notebooks and docs rather than the book.

| Day | Topic | Source | Book pp. | You will have |
| --- | --- | --- | --- | --- |
| Phase 0 - Pi bring-up (days 1-5) |  |  |  |  |
| 1 | Meet the Pi 4, flash the microSD, first SSH | IESTI05 C3 | 20-21, 25-27, 29-39 | Pi answers over SSH |
| 2 | Remote access: file transfer, remote desktop, two Pis and two networks | IESTI05 C3 | 38-44, 56-61 | Copy files both ways; desktop opened remotely |
| 3 | Linux command line | IESTI05 C2 (slides + linux_intro.pdf) | - | Navigate, edit, install, htop |
| 4 | Camera, swap memory, updates | IESTI05 C3 slide 10 | 43-55, 62-64 | First photo taken on the Pi |
| 5 | Python virtual environment + Jupyter on the Pi | IESTI05 C4 | 65-75 | Notebook running on the Pi |
| Phase 1 - ML foundations (Colab) (days 6-13) |  |  |  |  |
| 6 | Colab and Python review; what is TinyML | IESTI01 C2-C4b | - | Colab notebook running |
| 7 | The machine-learning paradigm | IESTI01 C5 | - | First model fitted |
| 8 | Neural-network building blocks | IESTI01 C6 | - | A small network in TensorFlow |
| 9 | Regression with a DNN | IESTI01 C7 | - | Regression model + plot |
| 10 | Classification with a DNN | IESTI01 C8 | - | Classifier + confusion matrix |
| 11 | Datasets, splits and metrics | IESTI01 C9 | - | Train/validation/test done right |
| 12 | Convolutions; image classification with a CNN | IESTI01 C10-C11 | - | CNN trained in Colab |
| 13 | Edge Impulse intro (Cifar-10); preventing overfitting | IESTI01 C12-C13 | - | Model trained in Edge Impulse |
| Phase 2 - Fixed-function AI on the Pi (days 14-26) |  |  |  |  |
| 14 | TensorFlow Lite + MobileNetV2 inference | IESTI05 C5 | 75-86 | Classify an image on the Pi |
| 15 | Live camera classification; a model trained from zero | IESTI05 C5 | 86-93 | Live classification from the camera |
| 16 | Custom classifier: goal and data collection | IESTI05 C6 | 94-102 | Your own dataset |
| 17 | Train in Edge Impulse | IESTI05 C7 | 103-111 | Trained, quantised model |
| 18 | Test, deploy and run live on the Pi | IESTI05 C7 | 112-130 | First custom classifier on the Pi |
| 19 | Object detection fundamentals | IESTI05 C8 | 131-145 | Pre-trained detector on an image |
| 20 | Pre-trained detectors and live stream | IESTI05 C8 | 146-153 | Live detection |
| 21 | Custom detection: data and labeling | IESTI05 C9 | 154-168 | Labeled dataset |
| 22 | SSD MobileNet in Edge Impulse; deploy | IESTI05 C10 | 169-187 | Detector on the Pi |
| 23 | FOMO (lightweight detection) | IESTI05 C10 | 188-202 | FOMO model on the Pi |
| 24 | YOLO with Ultralytics on the Pi | IESTI05 C11 | 203-219 | YOLO inference, NCNN export |
| 25 | YOLO: custom training and deployment | IESTI05 C12 | 220-237 | Custom YOLO model |
| 26 | Counting objects (bees) + Part 1 mini-project | IESTI05 C13-C14, Part 1 assignment | 238-264 | Counting pipeline |
| Phase 3 - Generative AI on the Pi (days 27-38) |  |  |  |  |
| 27 | Text generation with an RNN (VerneBot) | IESTI05 C15 | 265-289 | Tiny text generator |
| 28 | Knowledge distillation in practice | book chapter | 290-308 | Distilled model |
| 29 | Small language models: first model with Ollama | IESTI05 C16-C17 | 309-335 | SLM answering on the Pi |
| 30 | Ollama with Python | IESTI05 C18 | 336-360 | Python chat script |
| 31 | Function (tool) calling | IESTI05 C19 | 361-375 | SLM calling a Python function |
| 32 | Retrieval-augmented generation (RAG) | IESTI05 C20 | 376-388 | Question answering over your documents |
| 33 | Agents with small models | IESTI05 C20a | 560 onward | Simple tool-using agent |
| 34 | Vision-language models (Florence-2) | book chapter | 389-433 | Image captioning on the Pi |
| 35 | Audio and vision AI pipeline | book chapter | 434-458 | Speech in, answer out |
| 36 | GPIO and physical computing: LEDs, buttons | IESTI05 C21 | 459-485 | LED and button under code control |
| 37 | Sensors and notebooks | IESTI05 C21 | 486-510 | Sensor readings logged |
| 38 | SLMs for IoT control | IESTI05 C22 | 511-557 | A language model switching hardware |
| Phase 4 - TinyML applications (days 39-42) |  |  |  |  |
| 39 | Anomaly detection and K-means | IESTI01 C21-C22 | - | Anomaly detector (concept + notebook) |
| 40 | Keyword spotting (concepts) | IESTI01 C23-C24 | - | KWS pipeline understood |
| 41 | Image apps on microcontrollers; data collection | IESTI01 C25-C27 | - | Person detection concept |
| 42 | Responsible AI; going further with Edge AI | IESTI01 C28-C29 | - | Checklist for responsible deployment |
| Phase 5 - Capstone + teaching plan (days 43-46) |  |  |  |  |
| 43 | Choose and plan the project | IESTI05 Part 1 / Part 2 assignments | - | One-page project plan |
| 44 | Build | - | - | Working prototype |
| 45 | Build, test and measure | - | - | Measured results (honest ones) |
| 46 | Present, write up, and plan how to teach it | - | - | Report + teaching plan |
| Phase 6 - Optional: Arduino UNO Q (days 47-56) |  |  |  |  |
| 47 | UNO Q: foundations and setup | IESTI05 UNO Q Ch0-Ch1 | - | Board working |
| 50 | SLMs on the UNO Q; benchmarking; Python | IESTI05 UNO Q Ch2 (C19-C21) | - | Model running |
| 53 | Multimodal and agentic AI | IESTI05 UNO Q Ch3, Ch5 | - | Agent running |
| 55 | Physical AI: Bridge between the two processors | IESTI05 UNO Q Ch4 | - | Language model driving hardware |

NOTE Checkpoints (what you can show a student) • Day 5: a Pi you can log into from either laptop, with Python and Jupyter ready. • Day 13: a CNN you trained yourself. Day 18: your own image classifier running live on the Pi. • Day 26: YOLO counting objects. Day 32: a question-answering system over your own documents (RAG). • Day 38: a small language model switching real hardware. Day 46: your capstone and the plan to teach it.